## ai tool request pipel
AI Tool Request Pipeline
📥 New Requests (Intake phase/ Analysis + Scoring)
Name | Subitems | Requesting Stakeholder | Department Budget | Reviewed By | Target Quarter Date Release | Estimated Budget | Potential Tool Name/ Phase of Exploring Tools | Evaluation Status | Prioritization Status | Total Priority Score | Target Success Metric | Tools to be compared/piloted Notes
Lead/ Funnel AI Tooling |  | Bus Dev/ Revenue | Not Assigned Yet | Ankita Avadhani | Not Assigned Yet |  | Clay AI | Budget Evaluation | P1
Clio Data Copilot | Airia,Clio Duo Test | Briefly + All Firm | Not Assigned Yet | Ankita Avadhani | Not Assigned Yet |  | Clio Duo | Budget Evaluation | P1
Subitems | Name | Owner | Status | Date
| Airia |  | In Progress
| Clio Duo Test |  | In Progress
Managing Collections |  | Briefly + All Firm | Not Assigned Yet | Monica Goyal | Not Assigned Yet |  | Caddi/Airia? | Tool Discovery Phase | P0
AR: Automation ccounting firm scaling, manual bookkeeping overhead Annalee |  | Finance/ Accounting | Not Assigned Yet | Ankita Avadhani, Monica Goyal | Not Assigned Yet |  | Discovery Phase | Tool Discovery Phase | P0
No Code SQL + Python Queries | Cursor,Windsurf | IT | Not Assigned Yet | Ankita Avadhani | Not Assigned Yet |  | Cursor | Budget Evaluation | P1
Subitems | Name | Owner | Status | Date
| Cursor |  | In Progress
| Windsurf |  | In Progress
Origination + Accounting Scale |  | Scale Leadership | Not Assigned Yet | Ankita Avadhani, Monica Goyal | Not Assigned Yet |  | Spiff Replacement | Budget Evaluation | P1
Manual receipt capture, accounting integration gaps |  | Rimon Leadership | Not Assigned Yet | Ankita Avadhani, Monica Goyal | Not Assigned Yet |  | Dext (Receipt Bank) | Budget Evaluation | P0
Predictive Financial Forecasting (High Priority) |  | Finance/ Accounting | Not Assigned Yet | Ankita Avadhani | Q3 2025 |  |  | Budget Evaluation | NA
Email Management & Filtering for AP Team |  | Finance/ Accounting | Not Assigned Yet | Ankita Avadhani | Q3 2025 |  |  | Budget Evaluation | NA
Data Management & Analysis Tools |  | Finance/ Accounting | Not Assigned Yet | Ankita Avadhani | Q3 2025 |  |  | Budget Evaluation | NA
OGC Josef Implementation | Engagement letter,draft conflict waivers,draft audit letters | Briefly + All Firm | Not Assigned Yet |  | Q2 2026 |  |  | Budget Evaluation | NA
Subitems | Name | Owner | Status | Date
| Engagement letter |  | In Progress
| draft conflict waivers |  | In Progress
| draft audit letters |  | In Progress
Billing Guidelines and create a chart/compilation of billing guideline provisions - all firms |  | Finance/ Accounting | Not Assigned Yet |  | Q2 2026 |  |  | Budget Evaluation | NA
Attorney Dashboard - what is lawyer working on? Billings per month and activity by month to month |  | Briefly + All Firm | Not Assigned Yet |  | Q2 2026 |  |  | Budget Evaluation | NA
Cient activity - from HubSpot |  | Bus Dev/ Revenue | Not Assigned Yet |  | Q2 2026 |  |  | Budget Evaluation | NA
45 day touch points with clients |  | Bus Dev/ Revenue | Not Assigned Yet |  | Q2 2026 |  |  | Budget Evaluation | NA
YTD earnings report by lawyer |  | Finance/ Accounting | Not Assigned Yet |  | Q2 2026 |  |  | Budget Evaluation | NA
Zapier Integrations |  | Not Assigned Yet | Not Assigned Yet |  | Q2 2026 |  |  | Budget Evaluation | NA
🔍 Under Leadership Review (Review w/Charles & Leadership Stakeholders )
Name | Subitems | Requesting Stakeholder | Department Budget | Reviewed By | Target Quarter Date Release | Estimated Budget | Potential Tool Name/ Phase of Exploring Tools | Evaluation Status | Prioritization Status | Total Priority Score | Target Success Metric | Tools to be compared/piloted Notes
No-Code AI Agents (Attorney Work) | Airia | Briefly Level | Not Assigned Yet | Ankita Avadhani, Monica Goyal | Not Assigned Yet |  | Wordware/DeepJudge/Harvey | Budget Evaluation | NA
Subitems | Name | Owner | Status | Date
| Airia |  | In Progress
No Code Agents Across Backoffice | Airia | Briefly Level | Not Assigned Yet | Ankita Avadhani, Monica Goyal | Q4 2025 | $1000 / month unlimited users | Airia | Tool Evaluation | NA | 40 | Reduce overall manual Briefly manual back office tasks by 10% through no code agents
Subitems | Name | Owner | Status | Date
| Airia |  | In Progress
Microsoft Copilot Request |  | Briefly + All Firm | Not Assigned Yet | Monica Goyal | Not Assigned Yet | $30/user/month | Microsoft CoPilot | Budget Evaluation | NA | 43 | Efficiency with back office administration work. Example include note taking for meeting, searching for emails, email generation, Word generation, research, agent creation
✅ Approved - P0 (Critical priority)
Name | Subitems | Requesting Stakeholder | Department Budget | Reviewed By | Target Quarter Date Release | Estimated Budget | Potential Tool Name/ Phase of Exploring Tools | Evaluation Status | Prioritization Status | Total Priority Score | Target Success Metric | Tools to be compared/piloted Notes
Second Nature ¦ AI Role sales BD Hippler |  | Bus Dev/ Revenue | Bus Dev/ Revenue | Ankita Avadhani | Q1 2026 | $12,000 | Exploration of Sales Coaching tools starting with Second Nature | Priority Approved | P0 | 43
Finance App Builder – Decipad Replacement |  | Finance/ Accounting | Not Assigned Yet | Monica Goyal | Not Assigned Yet |  | Decipad (for now) | Pilot | P0 | 43 |  | Decipad has gone out of business. We will need to do some investigation for similar too
Client Onboarding Scale |  | Scale Leadership | Not Assigned Yet |  | Q2 2026 |  | Josef | Budget Evaluation | NA
Tool Proposed to Stakeholder: Done
Name | Subitems | Requesting Stakeholder | Department Budget | Reviewed By | Target Quarter Date Release | Estimated Budget | Potential Tool Name/ Phase of Exploring Tools | Evaluation Status | Prioritization Status | Total Priority Score | Target Success Metric | Tools to be compared/piloted Notes
BD LinkedIn automation and list building, social media posting | Postalize | Bus Dev/ Revenue | Not Assigned Yet | Monica Goyal | Not Assigned Yet |  | Postilize | Tool Evaluation | NA |  |  | Michael Curci to review in mid September
Subitems | Name | Owner | Status | Date
| Postalize |  | Done
Marketing Events Calendar/Social Calendar | MS CoPilot,Notion | Marketing | Marketing | Ankita Avadhani | Not Assigned Yet |  | Exploring Tools | Tool Discovery Phase | P2 |  |  | notion, copilot, ect
Subitems | Name | Owner | Status | Date
| MS CoPilot | Ankita Avadhani | Evaluating Tool
| Notion | Ankita Avadhani | Evaluating Tool
Workflow Process Automation | Claude Demo + Mermaid JS for Finance Team Train ing,Proposal | Finance/ Accounting | Not Assigned Yet | Ankita Avadhani | Q3 2025 |  |  | Budget Evaluation | NA
Subitems | Name | Owner | Status | Date
| Claude Demo + Mermaid JS for Finance Team Train ing | Ankita Avadhani | Training Complete | 2025-08-27
| Proposal |  | In Progress
⚡ Approved - P1 (Important priority)
Name | Subitems | Requesting Stakeholder | Department Budget | Reviewed By | Target Quarter Date Release | Estimated Budget | Potential Tool Name/ Phase of Exploring Tools | Evaluation Status | Prioritization Status | Total Priority Score | Target Success Metric | Tools to be compared/piloted Notes
📋 Approved - P2 (Future consideration)
Name | Subitems | Requesting Stakeholder | Department Budget | Reviewed By | Target Quarter Date Release | Estimated Budget | Potential Tool Name/ Phase of Exploring Tools | Evaluation Status | Prioritization Status | Total Priority Score | Target Success Metric | Tools to be compared/piloted Notes
❌ Rejected/Deferred
Name | Subitems | Requesting Stakeholder | Department Budget | Reviewed By | Target Quarter Date Release | Estimated Budget | Potential Tool Name/ Phase of Exploring Tools | Evaluation Status | Prioritization Status | Total Priority Score | Target Success Metric | Tools to be compared/piloted Notes
Hubspot Copilot |  | Bus Dev/ Revenue | Not Assigned Yet | Ankita Avadhani | Not Assigned Yet |  | GPT Integrations | Budget Evaluation | P1
Enterprise GPT Subscription |  | Briefly Level | Not Assigned Yet | Ankita Avadhani | Not Assigned Yet |  | Chat GPT Enterprise | Budget Evaluation | P2
Clio Duo |  | Briefly + All Firm | Not Assigned Yet |  | Q2 2026 |  |  | Budget Evaluation | NA
✨ Completed
Name | Subitems | Requesting Stakeholder | Department Budget | Reviewed By | Target Quarter Date Release | Estimated Budget | Potential Tool Name/ Phase of Exploring Tools | Evaluation Status | Prioritization Status | Total Priority Score | Target Success Metric | Tools to be compared/piloted Notes